## MICA Risk Assessment
Risk Assesement on the Implementation of MICA Health Solutions to Amic Hospital
S/N | What is the risk?* | Risk Score
1 | How long will it take to implement the proposed project: 1 - 6 months (1) 7 - 9 months (10) 10 - 12 months (50) 13 - 18 months (100) 19 - 24 months (250) Greater than 24 months (500) | 50
2 | What are the estimated project costs: $25,000 - $75,000 (1) $75,001 - $150,000 (10) $150,001 - $250,000 (50) $250,001 - $500,000 (100) $500,001 - $1,000,000 (250) $1,000,001 - $3,000,000 (500) greater than $3,000,000 (1000) | 500
3 | Degree of anticpated change to exisiting business processes: Low (1) Medium (10) High (100) Very High (250) | 10
4 | Number of employees impacted by the system: 1 - 20 (1) 21 - 50 (10) 51 - 100 (50) 101 - 250 (100) 251 - 500 (250) 501 - 1000 (500) greater than 1000 (1000) | 250
5 | Number of agencies impacted by the system: One (1) Two - Three (50) Four - Eight (100) Greater than Eight (250) | 50
6 | Anticipated user attitude to the new process/system: Very favorable (1) Favorable (10) Neutral (100) Unfavorable (250) Very unfavorable (500) | 1
7 | Number of exisiting applications that must feed or receive data from the new system: 0 (1) 1 (10) 2 - 3 (100) 4 - 5 (250) Greater than 5 (500) | 100
8 | Volume of required data to be converted from existing system to new system: None (1) 1 - 10,000 records (10) 10,001 - 50,000 records (50) 50,001 - 100,000 records (100) 100,001 - 250,000 records (250) Greater than 250,000 records (500) | 100
9 | Complexity of the required conversion: No conversion required (1) Low (100) Medium (250) High (500) | 1
10 | Will the system be implemented with an off-the-shelf system: Partially (100) Totally (250) No (500) | 100
11 | Has the hospital developed /implemented systems similar in size and complexity in the past: Yes (1) No (500) | 1
12 | Project teams level of expereince with the bussiness process being impacted: High (1) Medium (100) Low (250) | 100
13 | Hosiptal Staff experience with implementing systems with similar technologies: High (1) Medium (100) Low (250) | 1
14 | Support of Department Head and Senior Managers in the hospital: High (1) Medium (100) Low (500) | 1
15 | Other external entity involve in the project: No external entity is involved (1) External entity is playing a minor role (250) External entity is an equal partner in the project (500) External entitiy is primarily in control of the project (1,000) | 250
| Total | 1515
Risk Assessment Scoring Tool
| Impact | Score
| Very Low | 113 - 1,000
| Low | 1,001 - 2,500
| Medium | 2,501 - 5,000
| High | 5,001 - 6,500
| Very High | 6,501 - 7,750