## Requirements
Feature | Req ID | Requirements
Patient Portal & Engagement | REQ_01 | Patient account registration with personal and health-related info.
| REQ_02 | Book appointments online.
| REQ_03 | View medical history and clinical records.
| REQ_04 | Messaging portal to communicate with healthcare providers.
| REQ_05 | Automated appointment reminders via email and SMS.
| REQ_06 | Online payments for bills.
| REQ_07 | Upload scanned physical medical documents.
| REQ_08 | Reschedule appointments online.
| REQ_09 | Cancel appointments online.
Doctor & Clinical Operations Management | REQ_10 | Doctors access real-time patient health records.
| REQ_11 | Doctors update patient health records.
| REQ_12 | Digital prescriptions.
| REQ_13 | Real-time triage and prioritization.
| REQ_14 | Decision support for prescriptions.
| REQ_15 | Assign healthcare providers to patients.
| REQ_16 | Discharge management and summaries.
Hospital Administration & Management | REQ_05 | Integration with hospital systems (patient management, billing, inventory).
| REQ_06 | Generate invoices.
| REQ_07 | Auto-update inventory on usage.
| REQ_08 | Clinical management tools for scheduling and record tracking.
| REQ_09 | Data-driven insights for patient care and operations.
| REQ_10 | Centralized dashboard for administrators.
| REQ_11 | Generate clinical, financial, operational reports.
| REQ_12 | Search patients, appointments, medical records.
| REQ_13 | Integrate with external systems for referrals and records.
Security, Compliance & Access Control | REQ_07 | Role-based access control.
| REQ_08 | Multi-factor authentication.
| REQ_09 | Export medical records compliant with regulations.
| REQ_10 | HIPAA-compliant data storage/processing.
| REQ_11 | Track/log patient record changes.
| REQ_12 | Notify doctors on patient data updates.
| REQ_13 | Automatic backups.
| REQ_14 | Compliance with HIPAA & regulations.
| REQ_15 | Automated monthly security audits.
| REQ_16 | Secure user activity logs.
System Performance, Availability & Reliability | REQ_17 | 99.9% uptime.
| REQ_18 | <2 sec response time for records.
| REQ_19 | Scalable for future growth.
| REQ_20 | Recovery time objective of 4 hours.
| REQ_21 | High availability infra to minimize maintenance downtime.
| REQ_22 | <0.01% failure in medical record updates.
| REQ_23 | Page load ≤3 seconds.
| REQ_24 | Clear error messages.

## EPICS
Feature | US_ID | EPIC
Patient Portal & Engagement | US_01 | As a Patient, I want to access a secure online health portal where I can register my account, manage appointments, view my medical records, communicate with my healthcare providers, receive automated reminders, make online payments, and upload important documents, so that I can conveniently manage my healthcare needs in one place.
Doctor & Clinical Operations Management | US_02 | As a doctor or healthcare provider, I want to seamlessly access and update real-time patient health records, prescribe medications digitally, receive intelligent decision support for prescriptions, manage patient triage and prioritization during emergencies, oversee patient discharge processes including summaries, and be assigned patients based on my availability and specialty, so that I can deliver timely, accurate, and high-quality care, optimize clinical workflows, and ensure the best possible patient outcomes.
Hospital Administration & Management | US_03 | As a Hospital Administrator, I want an integrated platform that connects patient management, billing, inventory, clinical tools, and external systems, so that I can efficiently oversee hospital operations, ensure quality patient care, and make data-driven decisions.
Security, Compliance & Access Control | US_04 | As a Healthcare Administrator, I want the system to enforce robust security controls, maintain HIPAA compliance, and ensure data integrity through access restrictions, auditing, secure storage, and notifications, so that patient health data remains protected, compliant with regulations, and trustworthy.
System Performance, Availability & Reliability | US_05 | As a Healthcare IT Administrator, I want the health platform to be highly available, fast, scalable, and resilient, so that patients and healthcare providers can always access accurate medical data without delays or interruptions.

## User Stories
ID | User Story Title | User Story Description | Relates to Epic | Acc_ID | Acceptance Criteria
US-06 | Patient Account Registration | As a Patient, I want to create a secure account with my personal and health-related information, so that I can access and manage my healthcare services online. | US_01 | AC-06-01 | Given that I am on the registration page, When I enter valid personal and health-related details and submit, Then my account is created and I receive a confirmation email.
|  |  |  | AC-06-02 | Given that I submit incomplete or invalid information, When I try to register, Then I am shown appropriate error messages and prompted to correct the data.
US-07 | Book Appointments Online | As a Patient, I want to book appointments with healthcare providers online so that I can conveniently schedule my visits. | US_01 | AC-07-01 | Given that I am logged into the portal, When I select a provider and available date/time and confirm, Then my appointment is booked and I receive a confirmation email/SMS.
|  |  |  | AC-07-02 | Given that the selected slot is no longer available, When I try to book it, Then I am prompted to choose a different available slot.
US-08 | View Medical History and Clinical Records | As a Patient, I want to view my past medical history and clinical records online so that I can stay informed about my health status. | US_01 | AC_08_01 | Given that I am logged into the portal, When I navigate to the medical history section, Then I can see a list of my past diagnoses, treatments, and lab results.
|  |  |  | AC_08_02 | Given that my records are still being processed, When I access the section, Then I see a message indicating that records are being updated.
US-09 | Messaging with Healthcare Providers | As a Patient, I want to send and receive secure messages with my healthcare providers so that I can get answers to my health-related questions. | US_01 | AC_09_01 | Given that I am logged in, When I send a message through the portal, Then my provider receives it and I see it in my message history.
|  |  |  | AC_09_02 | Given that I receive a reply from my provider, When I check my messages, Then I can view the response and get notified via email/SMS.
US-10 | Automated Appointment Reminders | As a Patient, I want to receive automated appointment reminders via email and SMS so that I do not miss my scheduled visits. | US_01 | AC_10_01 | Given that I have an upcoming appointment, When the reminder interval is reached (e.g., 24 hours before), Then I receive an email and SMS reminder with appointment details.
US-11 | Online Payments for Bills | As a Patient, I want to pay my healthcare bills online so that I can quickly settle payments without visiting the hospital. | US_01 | AC_11_01 | Given that I have a pending bill, When I choose to pay online and complete the payment, Then I receive a confirmation and my billing history updates.
|  |  |  | AC_11_02 | Given that my payment fails, When I attempt to pay, Then I receive an error message with options to retry.
US-12 | Reschedule Appointments | As a Patient, I want to reschedule my appointments online so that I can adjust them to fit my availability. | US_01 | AC_12_01 | Given that I have an existing appointment, When I select a new date/time and confirm, Then my appointment is updated and I receive a new confirmation.
US-13 | Cancel Appointments | As a Patient, I want to cancel appointments online so that I can notify the clinic when I cannot attend. | US_01 | AC_13_01 | Given that I have an existing appointment, When I choose to cancel it, Then the appointment is removed and I receive a cancellation confirmation.
US-14 | Upload Medical Documents | As a Patient, I want to upload scanned copies of physical medical documents so that my healthcare provider can keep my records complete. | US_01 | AC_14_01 | Given that I am logged into the portal, When I upload a scanned document, Then it is securely saved and associated with my health record.
|  |  |  | AC_14_02 | Given that I upload an unsupported file type, When I try to submit, Then I receive an error message prompting me to upload a valid format.
US-15 | Access & Update Real-Time Patient Health Records | As a Doctor, I want to access and update patient health records in real-time so that I can make informed decisions and keep records accurate. | US_02 | AC_15_01 | Given that I am logged into the system, When I open a patient’s record, Then I can view up-to-date medical history, lab results, and treatment plans.
|  |  |  | AC_15_02 | Given that I update a patient’s record, When I save the changes, Then the record reflects the updates instantly and is accessible by other authorized staff.
US-16 | Digital Prescriptions | As a Doctor, I want to prescribe medications digitally so that I can streamline the prescription process and reduce errors. | US_02 | AC_16_01 | Given that I have completed a patient assessment, When I prescribe medication through the system, Then the prescription is saved to the patient’s record and sent to the pharmacy electronically.
|  |  |  | AC_16_02 | Given that I enter an incompatible dosage or medication, When I try to submit, Then the system alerts me to review and correct it.
US-17 | Intelligent Decision Support for Prescriptions | As a Doctor, I want to receive decision support recommendations when prescribing medications so that I can avoid contradications and improve patient safety. | US_02 | AC_17_01 | Given that I select a medication for a patient, When there are known allergies or interactions, Then the system displays alerts and suggests alternatives.
US-18 | Manage Patient Triage & Prioritization | As a Doctor, I want to view and manage patient triage information so that I can prioritize critical cases during emergencies. | US_02 | AC_18_01 | Given that new patients are checked into the ER, When I view the triage dashboard, Then I see patients sorted by urgency with color-coded statuses.
US-19 | Oversee Patient Discharge & Summaries | As a Doctor, I want to finalize discharge summaries and instructions so that patients leave with clear follow-up care plans. | US_02 | AC_19_01 | Given that a patient is ready for discharge, When I complete the discharge form and summary, Then it is stored in the patient record and printed or emailed to the patient.
US-20 | Be Assigned Patients Based on Availability & Specialty | As a Doctor, I want to be assigned patients based on my schedule and specialty so that workloads are balanced and patients get appropriate care. | US_02 | AC_20_01 | Given that a new patient needs assignment, When the system checks doctor availability and specialties, Then the patient is assigned to the most suitable available doctor.
0

## Gantt Chart
| Project : | Resource | Duration | Start | End | Sprint 1 | [13 empty] | Sprint 2 | [13 empty] | Sprint 3 | [13 empty] | Sprint 4 | [13 empty] | Sprint 5 | [13 empty] | Sprint 6 | [13 empty] | Sprint 7 | [13 empty] | Sprint 7
Ref | Phase, User Story/Task | Role or person | Days | Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
UA_01 | Patient Portal & Engagement |  | 63 | 01/06/2026 | 19/08/2024
US_06 | Patient Account Registration
TSK_06_01 | Design Registration Form | Web Designer | 3 | 01/06/2026 | 04/06/2024
TSK_06_02 | Frontend form implementation | Software Engineer | 5 | 05/06/2024 | 10/06/2024
TSK_06_03 | Backend API for user creation | Software Engineer | 5 | 11/06/2024 | 16/06/2024
TSK_06_04 | Validate personal & health info | Software Engineer | 1,5 | 17/06/2024 | 18/06/2024
TSK_06_05 | Store in secure DB | Database Analyst | 0,5 | 17/06/2024 | 17/06/2024
US_07 | Book Appointments Online
TSK_07_01 | Appointment calendar UI | Web Designer | 2 | 18/06/2024 | 20/06/2024
TSK_07_02 | Frontend implementation | Software Engineer | 5 | 21/06/2024 | 26/06/2024
TSK_07_03 | Doctor availability logic | Software Engineer | 5 | 27/06/2024 | 01/07/2024
TSK_07_04 | Confirm & store appointments | Software Engineer | 3 | 2024-02-07 | 05/07/24
US_08 | View Medical History and Clinical Records
TSK_08_01 | Build Medical Records UI | Web Designer | 2 | 2024-06-07 | 2024-08-07
TSK_08_02 | Frontend form implementation | Software Engineer | 5 | 2024-09-07 | 13/7/2024
TSK_08_03 | Fetch data from HER | Software Engineer | 0,5 | 14/7/2024 | 14/7/2024
TSK_08_04 | Add search/filter feature | Software Engineer | 3 | 15/7/2024 | 17/7/2024
US_09 | Messaging with Healthcare Providers
TSK_09_01 | Messaging interface | Software Engineer | 2 | 18/7/2024 | 20/7/2024
TSK_09_02 | Real-time or secure message API | Software Engineer | 3 | 21/7/2024 | 23/7/2024
TSK_09_03 | Notifications for new messages | Software Engineer | 3 | 24/7/2024 | 26/7/2024
US_10 | Online Payments for Bills
TSK_10_01 | Integrate payment gateway | Software Engineer | 3 | 27/7/2024 | 29/7/2024
TSK_10_02 | View billing history | Software Engineer | 2 | 30/7/2024 | 2024-01-08
TSK_10_03 | Secure transaction logging | Software Engineer | 3 | 2024-02-08 | 2024-05-08
US_11 | Reschedule Appointments
TSK_11_01 | Appointment editing logic | Software Engineer | 2 | 2024-06-08 | 2024-08-08
TSK_11_02 | Conflict checking | Software Engineer | 3 | 2024-09-08 | 2024-11-08
TSK_11_03 | Notification trigger on change | Software Engineer | 1,5 | 2024-12-08 | 13/8/2024
US_12 | Cancel Appointments
TSK_12_01 | Add cancel option | Software Engineer | 0,5 | 14/8/2024 | 14/08/2024
TSK_12_02 | Define cancellation policy | Business Analyst | 2 | 15/08/2024 | 16/08/2024
TSK_12_03 | Update availability slots | Software Engineer | 2 | 17/08/2024 | 19/08/2024
UA_02 | Doctor & Clinical Operations Management |  | 47 | 20/8/2024 | 11/10/2024
US_15 | Access & Update Real-Time Patient Health Records
TSK_15_01 | Real-time record update | Software Engineer | 2 | 20/8/2024 | 22/8/2024
TSK_15_02 | Role-based access control | Software Engineer | 2 | 23/8/2024 | 25/8/2024
TSK_15_03 | Audit log | Software Engineer | 2 | 25/8/2024 | 27/9/2024
US_16 | Digital Prescriptions
TSK_16_01 | Prescription form UI | Web Designer | 2 | 28/8/2024 | 30/8/2024
TSK_16_02 | Drug database integration | Software Engineer | 5 | 31/8/2024 | 2024-04-09
TSK_16_03 | Send prescription to pharmacy | Software Engineer | 2 | 2024-05-09 | 2024-07-09
US_17 | Intelligent Decision Support for Prescriptions
TSK_17_01 | AI rule engine or alert system | Software Engineer | 2 | 2024-08-09 | 2024-10-09
TSK_17_02 | Drug Interaction Checker | Software Engineer | 5 | 2024-11-09 | 16/9/2024
TSK_17_03 | Recommendations based on history | Data Analyst | 3 | 17/9/2024 | 19/9/2024
US_18 | Manage Patient Triage & Prioritization
TSK_18_01 | Triage form UI | Web Designer | 2 | 20/9/2024 | 21/9/2024
TSK_18_02 | Priority assignment logic | Software Engineer | 3 | 22/9/2024 | 25/9/2024
TSK_18_03 | Dashboard for high-risk cases | Web Designer | 2 | 17/9/2024 | 19/9/2025
US_19 | Oversee Patient Discharge & Summaries
TSK_19_01 | Discharge summary form | Web Designer | 0,5 | 20/9/2024 | 20/9/2024
TSK_19_02 | Auto-generate from HER | Software Engineer | 3 | 24/9/2024 | 26/9/2024
TSK_19_03 | Export/print/download option | Software Engineer | 3 | 27/9/2024 | 29/9/2025
US_20 | Be Assigned Patients Based on Availability & Specialty
TSK_20_01 | Doctor assignment algorithm | Software Engineer | 2 | 30/9/2024 | 2024-02-10
TSK_20_02 | Specialty matching | Software Engineer | 5 | 2024-03-10 | 2024-08-10
TSK_20_03 | Real-time calendar sync | Software Engineer | 2 | 2024-09-10 | 2024-11-10

## Traceability Matrix
Feature | Req ID | Requirements | User Story IDs | Task IDs | TEST Ids | Test Execution notes
Patient Portal & Engagement | REQ_01 | Patient account registration with personal and health-related info. | US-06 | TSK_06_01,TSK_06_02,TSK_06_03,TSK_06_04,TSK_06_05 | AC-06-01,AC-06-02
| REQ_02 | Book appointments online. | US-07 | TSK_07_01,TSK_07_02, TSK_07_03,TSK_07_04 | AC-07-01,AC-07-02
| REQ_03 | View medical history and clinical records. | US-08 | TSK_08_01,TSK_08_02, TSK_08_03 | AC-08-01,AC-08-02
| REQ_04 | Messaging portal to communicate with healthcare providers. | US-09 | TSK_09_01,TSK_09_02 | AC-09-01,AC-09-02
| REQ_05 | Automated appointment reminders via email and SMS. | US-10 | TSK_09_03 | AC-10-01
| REQ_06 | Online payments for bills. | US-11 | TSK_11_01,TSK_11_02, TSK_11_03 | AC-11-01,AC-11-02
| REQ_08 | Reschedule appointments online. | US-12 | TSK_12_01,TSK_12_02, TSK_12_03 | AC-12-01,AC-12-02
| REQ_09 | Cancel appointments online. | US-13 | TSK_13_01,TSK_13_02, TSK_13_03 | AC-13-01,AC-13-02
| REQ_07 | Upload scanned physical medical documents. | US-14 |  | AC-13-01,AC-13-02
Doctor & Clinical Operations Management | REQ_10 | Doctors access real-time patient health records. | US-15 | TSK_15_01,TSK_15_02, TSK_15_03 | AC-15-01,AC-15-02
| REQ_12 | Digital prescriptions. | US-16 | TSK_16_01,TSK_16_02, TSK_16_03 | AC-16-01,AC-16-02
| REQ_14 | Decision support for prescriptions. | US-17 | TSK_17_01,TSK_17_02, TSK_17_03 | AC-17-01
| REQ_13 | Real-time triage and prioritization. | US-18 | TSK_18_01,TSK_18_02, TSK_18_04 | AC-18-01
| REQ_16 | Discharge management and summaries. | US-19 | TSK_19_01,TSK_19_02, TSK_19_03 | AC-19-01
| REQ_15 | Assign healthcare providers to patients. | US-20 | TSK_20_01,TSK_20_02, TSK_20_03 | AC-20-01